## Sheet 1
Capital Site Improvement Projects
Status Report as of
|  | Project |  |  |  | Estimated |  | Adjusted | Amount |  |  |  | Code
|  | Code |  | Responsible |  | Completion | Budget | Project | Paid To | Balance To | Budget |  | D=done
Location |  | Number |  | Party | Task Description | Date | Amount | Amount | Date | Complete | Variance | Comments | I=incomplete
District Wide | 0 | - | 1 | Contractor | Project 1 |  | 10000 | 17500 | 17462 | 38 | -7500 | In Durant Project | I
| 0 | - | 2 | Contractor | Project 2 | Completed | 2000 | 2000 | 3275 | -1275 | 0 |  | I
| 0 | - | 3 | Contractor | Project 3 | Completed | 6000 | 3250 | 5180 | -1930 | 2750 |  | I
| 0 | - | 4 |  | Project 4 |  | 10000 | 6000 | 17725 | -11725 | 4000
[5 empty] | DISTRICT WIDE TOTAL |  | 28000 | 28750 | 43642 | -14892 | -750
High School | 1 | - | 1 | Contractor | Project 1 | Completed | 7000 | 7000 | 0 | 7000 | 0 |  | C
| 1 | - | 2 |  | Project 2 |  | 7000 | 7000 | 0 | 7000 | 0
| 1 | - | 3 | Both |  | 4/1/98 | 0 | 0 | 0 | 0 | 0 | Waiting on paint order | I
| 1 | - | 4 |  |  |  | 0 | 0 | 0
[5 empty] | HIGH SCHOOL TOTAL |  | 14000 | 14000 | 0 | 14000 | 0
Middle School | 3 | - | 1 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | MIDDLE SCHOOL TOTAL |  | 0 | 0 | 0 | 0 | 0
Elementary School | 6 | - | 1 | Contractor | Project 1 | Completed | 6000 | 5500 | 5500 | 0 | 500 |  | I
| 6 | - | 2 |  | Proejct 2 |  | 4500 | 3700 | 3683 | 17 | 800
| 6 | - | 3 |  | Project 3 |  | 2500 | 2500 | 4012 | -1512 | 0
| 6 | - | 4 |  |  |  | 0 | 0 | 0 | 0 | 0
| 6 | - | 5 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | ELEMENTARY SCHOOL TOTAL |  | 13000 | 11700 | 13195 | -1495 | 1300
[5 empty] | TOTALS |  | 55000 | 54450 | 56837 | -2387 | 550 | #REF! | #REF!
Note on J11: Jim Graham: less 8300 plus 2413, 3990, and 2993.