## Report
BOND 2003 TECHNOLOGY BUDGET REPORT
For the Month Ended February 28, 2006
|  | Budget |  |  | Actual/Adjusted Amount
[7 empty] | Paid to | Balance to |  | Amount | Remaining
Project | Unit Price | Qty | Budget | Unit Price | Qty | Budget | Date | Complete | Variance | Committed | Uncommitted
SERIES I
Elementary - Special Ed
Computers | 1100 | 30 | 33000 | 1100 | 45 | 52190 | 55457 | -3267 | -19190 | 55457 | -3267
Printers/Other |  |  | 11100 |  |  | 33000 | 35476 | -2476 | -21900 | 35476 | -2476
Telephone System |  |  | 15000 |  |  | 14000 | 14510 | -510 | 1000 | 14510 | -510
Building Infrastructure/Monitors | 28000 | 1 | 28000 | 23000 | 1 | 23000 | 16290 | 6710 | 5000 | 16290 | 6710
Network Electronics | 4100 | 1 | 4100 | 4500 | 1 | 4500 | 4378 | 122 | -400 | 4378 | 122
TOTAL |  |  | 91200 |  |  | 126690 | 126111 | 579 | -35490 | 126111 | 579
Salem
Office | 1500 | 1 | 1500 | 4000 | 1 | 4000 | 3965 | 35 | -2500 | 3965 | 35
Other Projects | 2500 | 1 | 2500 | 0 | 1 | 0 | 0 | 0 | 2500 | 0 | 0
TOTAL |  |  | 4000 |  |  | 4000 | 3965 | 35 | 0 | 3965 | 35
Millennium Tech Wing
Modules | 25000 | 1 | 25000 | 27230 | 1 | 27230 | 27230 | 0 | -2230 | 27230 | 0
Telephone System | 2500 | 1 | 2500 | 300 | 1 | 300 | 285 | 15 | 2200 | 285 | 15
WAN relocation | 31530 | 1 | 31530 | 27500 | 1 | 27500 | 27502 | -2 | 4030 | 27502 | -2
TOTAL |  |  | 59030 |  |  | 55030 | 55017 | 13 | 4000 | 55017 | 13
New Maint/Transp Building
Computers | 800 | 15 | 12000 | 800 | 15 | 12000 | 0 | 12000 | 0 | 0 | 12000
Printers/Other | 10000 | 1 | 10000 | 10000 | 1 | 10000 | 0 | 10000 | 0 | 0 | 10000
Telephone System | 13000 | 1 | 13000 | 13000 | 1 | 13000 | 0 | 13000 | 0 | 0 | 13000
WAN relocation | 10000 | 1 | 10000 | 10000 | 1 | 10000 | 0 | 10000 | 0 | 0 | 10000
Building Infrastructure/Monitors | 20000 | 1 | 20000 | 20000 | 1 | 20000 | 0 | 20000 | 0 | 0 | 20000
TOTAL |  |  | 65000 |  |  | 65000 | 0 | 65000 | 0 | 0 | 65000
High School
Design/Techical Studies | 50000 | 1 | 50000 | 100000 | 1 | 100000 | 55606 | 44394 | -50000 | 55606 | 44394
Broadcast Studio | 0 | 1 | 0 | 80000 | 1 | 80000 | 26600 | 53400 | -80000 | 26600 | 53400
Special Ed IDF | 0 | 1 | 0 | 20000 | 1 | 20000 | 0 | 20000 | -20000 | 0 | 20000
Other Projects | 350000 | 1 | 350000 | 200000 | 1 | 200000 | 0 | 200000 | 150000 | 0 | 200000
TOTAL |  |  | 400000 |  |  | 400000 | 82206 | 317794 | 0 | 82206 | 317794
Computer/Printer Replacements
2005-06
Computers-Growth | 1100 | 25 | 27500 | 898 | 21 | 18858 | 18858 | 0 | 8642 | 18858 | 0
Computers-Elementary Staff | 1100 | 200 | 220000 | 1013.24 | 202 | 204848.48 | 202600 | 2248.48 | 15151.52 | 202600 | 2248.48
Computers-Special Ed Students |  |  |  | 898 | 49 | 44002 | 44002 | 0 | -44002 | 44002 | 0
Computers-HS Lab Replacements | 1100 | 150 | 165000 | 898 | 120 | 107760 | 107760 | 0 | 57240 | 107760 | 0
Computers-MS Lab Replacements | 1100 | 150 | 165000 | 898 | 180 | 161640 | 161640 | 0 | 3360 | 161640 | 0
Laptop Additions | 37500 | 7 | 262500 | 0 | 0 | 0 | 0 | 0 | 262500 | 0 | 0
AV Presentation Carts | 0 | 0 | 0 | 3000 | 11 | 0 | 0 | 0 | 0 | 0 | 0
Mini labs 6-12 |  |  |  | 898 | 70 | 62860 | 62860 | 0 | -62860 | 62860 | 0
Printers-Secondary | 225 | 160 | 36000 | 392.695 | 219 | 0 | 0 | 0 | 36000 | 0 | 0
2006-07
Computers-Growth | 1100 | 25 | 27500 | 1100 | 25 | 27500 | 0 | 27500 | 0 | 0 | 27500
Computers-Elementary Students | 1150 | 430 | 494500 | 1000 | 430 | 430000 | 0 | 430000 | 64500 | 0 | 430000
Computers-MacIntosh |  |  |  | 2950 | 15 | 44250 | 0 | 44250 | -44250 | 0 | 44250
Computers-MS Lab Replacements | 1100 | 60 | 66000 | 1100 | 60 | 66000 | 0 | 66000 | 0 | 0 | 66000
Printers-Network Lab Lasers | 1500 | 28 | 42000 | 1100 | 38 | 41800 | 0 | 41800 | 200 | 0 | 41800
TOTAL |  |  | 1506000 |  |  | 1209518.48 | 597720 | 611798.48 | 296481.52 | 597720 | 611798.48
WAN Upgrade
Upgrade Backbone | 200000 | 1 | 200000 | 200000 | 1 | 200000 | 0 | 200000 | 0 | 0 | 200000
Remaining Upgrades
Servers | 180000 | 1 | 180000 | 180000 | 1 | 180000 | 20566 | 159434 | 0 | 0 | 180000
Proxy Server | 18000 | 1 | 18000 | 18000 | 1 | 18000 | 3246 | 14754 | 0 | 3246 | 14754
Server | 18000 | 1 | 18000 | 18000 | 1 | 18000 | 0 | 18000 | 0 | 0 | 18000
Application Server | 25000 | 1 | 25000 | 25000 | 1 | 25000 | 0 | 25000 | 0 | 0 | 25000
Skyward Server | 25000 | 1 | 25000 | 25000 | 1 | 25000 | 0 | 25000 | 0 | 0 | 25000
Video Server | 65000 | 1 | 65000 | 65000 | 1 | 65000 | 0 | 65000 | 0 | 0 | 65000
TOTAL |  |  | 531000 |  |  | 531000 | 23812 | 507188 | 0 | 3246 | 527754
Fees/Contingency Series I
Technology Designer | 289200 | 1 | 289200 | 289200 | 1 | 289200 | 185509 | 103691 | 0 | 284400 | 4800
Contingency (5%) | 292680 | 1 | 292680 | 161905.5 | 1 | 161905.5 | 0 | 161905.5 | 130774.5 | 0 | 161905.5
TOTAL |  |  | 581880 |  |  | 451105.5 | 185509 | 265596.5 | 130774.5 | 284400 | 166705.5
TOTAL SERIES I |  |  | 3238110 |  |  | 2842343.98 | 1074340 | 1768003.98 | 395766.02 | 1152665 | 1689678.98
SERIES II
New High School
Computers | 1100 | 425 | 467500 | 1200 | 380 | 456000 | 0 | 456000 | 11500 | 0 | 456000
Laser Printers-Non Network | 340 | 75 | 25500 | 340 | 80 | 27200 | 0 | 27200 | -1700 | 0 | 27200
Laser Printers-Network | 505 | 75 | 37875 | 520 | 35 | 18200 | 0 | 18200 | 19675 | 0 | 18200
Laser-Color | 1955 | 10 | 19550 | 1955 | 6 | 11730 | 0 | 11730 | 7820 | 0 | 11730
Laptops | 1100 | 150 | 165000 | 15000 | 18 | 270000 | 0 | 270000 | -105000 | 0 | 270000
Access Points | 800 | 10 | 8000 | 800 | 13 | 10400 | 0 | 10400 | -2400 | 0 | 10400
Charging Stations | 950 | 10 | 9500 | 950 | 0 | 0 | 0 | 0 | 9500 | 0 | 0
File Server | 20000 | 1 | 20000 | 15000 | 1 | 15000 | 0 | 15000 | 5000 | 0 | 15000
WAN | 50000 | 1 | 50000 | 50000 | 1 | 50000 | 0 | 50000 | 0 | 0 | 50000
Building Infrastructure | 750000 | 1 | 750000 | 700000 | 1 | 700000 | 0 | 700000 | 50000 | 0 | 700000
Network Electronics | 75000 | 1 | 75000 | 70650 | 1 | 70650 | 0 | 70650 | 4350 | 0 | 70650
Video Studios/Electronics | 150000 | 1 | 150000 | 200000 | 1 | 200000 | 0 | 200000 | -50000 | 0 | 200000
Broadcast Studio/Radio | 200000 | 1 | 200000 | 200000 | 1 | 200000 | 0 | 200000 | 0 | 0 | 200000
Telephone System | 50000 | 1 | 50000 | 50000 | 1 | 50000 | 0 | 50000 | 0 | 0 | 50000
Miscellaneous | 200000 | 1 | 200000 | 150000 | 1 | 150000 | 0 | 150000 | 50000 | 0 | 150000
TOTAL |  |  | 2227925 |  |  | 2229180 | 0 | 2229180 | -1255 | 0 | 2229180
Fees/Contingency Series II
Technology Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency (5%) | 235620 | 1 | 235620 | 184765.875 | 1 | 184765.875 | 0 | 184765.875 | 50854.125 | 0 | 184765.875
TOTAL |  |  | 235620 |  |  | 184765.875 | 0 | 184765.875 | 50854.125 | 0 | 184765.875
TOTAL SERIES II |  |  | 2463545 |  |  | 2413945.875 | 0 | 2413945.875 | 49599.125 | 0 | 2413945.875
TOTALS |  |  | 5701655 |  |  | 5256289.855 | 1074340 | 4181949.855 | 445365.145 | 1152665 | 4103624.855
Note on C120: SLCS: Granger only shows $82,000, other $60K in BG budget